## ITemportfolio_website_project_t
Task | Start | End | Duration | Status
Executive Proposal | 2025-05-26 | 2025-06-01 | 6 | Not Started
Coaching & Communication Section | 2025-06-02 | 2025-06-15 | 13 | Not Started
Customer Service & Escalation Toolkit | 2025-06-16 | 2025-06-22 | 6 | Not Started
KPI Dashboard & Mini Budget | 2025-06-23 | 2025-07-06 | 13 | Not Started
Team Leadership & HR Templates | 2025-07-07 | 2025-07-20 | 13 | Not Started | Task ID | Task | Task Duration | Start Date | End Date
Ethics & Cultural Adaptation Plan | 2025-07-21 | 2025-08-03 | 13 | Not Started |  | Milestone 1: Communication & Coaching | 19 | 2025-05-26 | 2025-06-15
Final Website Design and Integration | 2025-08-04 | 2025-08-10 | 6 | Not Started |  | Executive Proposal | 6 | 2025-05-26 | 2025-06-01
Final Video Presentation and Publishing | 2025-08-11 | 2025-08-15 | 4 | Not Started |  | Coaching & Communication Section | 13 | 2025-06-02 | 2025-06-15
[6 empty] | Milestone 2: KPIs, Budget & Leadership | 32 | 2025-06-16 | 2025-07-20
[6 empty] | Customer Service & Escalation Toolkit | 6 | 2025-06-16 | 2025-06-22
[6 empty] | KPI Dashboard & Mini Budget | 13 | 2025-06-23 | 2025-07-06
[6 empty] | Team Leadership & HR Templates | 13 | 2025-07-07 | 2025-07-20
[6 empty] | Milestone 3: Ethics, Culture & Final Integration (August) | 23 | 2025-07-21 | 2025-08-15
[6 empty] | Ethics & Cultural Adaptation Plan | 13 | 2025-07-21 | 2025-08-03
[6 empty] | Final Website Design and Integration | 6 | 2025-08-04 | 2025-08-10
[6 empty] | Final Video Presentation and Publishing | 4 | 2025-08-11 | 2025-08-15